Post-Earthquake Reconstruction

of Schools in Nepal:

Design & Project Management for Reconstruction of 70 School Buildings and Library Facility

PROJECT EXECUTION MANUAL

Post-Earthquake Reconstruction

DONOR (DEVELOPMENT PARTNER):

FOR

PROJECT MANAGEMENT CONSULTANT

of Schools in Nepal:

Ministry of External Affairs

Government of India

New Delhi, India

Nepal Reconstruction Authority

Central Level Project Implementation Unit (Education)

Govt. of Nepal, Kathmandu

CSIR-Central Building Research Institute, Roorkee, India

Design & Project Management for Reconstruction / Retrofitting of 70 School Buildings and 2 Library Facilities

Introduction

Approval Sheet

| APPROVAL |  |
| --- | --- |
| Prepared By CBRI | Approved By CLPIU |

Table of Contents

| S. No. | Section | Page No. |
| --- | --- | --- |
| 01 | Introduction | 4 |
| 02 | About the Project | 5 |
| 03 | Processes | 9 |
|  | Section A – Initiation Phase | 10 |
|  | Section B – Planning Phase | 12 |
|  | Section C – Construction Phase | 15 |
|  | Section D – Closeout Phase | 25 |
|  | Section E – DLP Phase | 27 |
| 04 | Inspection Protocol | 29 |
| 05 | Mobile App based Reporting for Daily Monitoring | 32 |

Abbreviation

| CBRI CLPIU CSIR DLP DLPIU GOI GON MEA MEP MTC NCR NOC PEM PMC RA Bill SMC TL TUCL | Central Building Research Institute Central Level Project Implementation Unit Council for Scientific & Industrial Research Defect Liability Period District Level Project Implementation Unit Govt. of India Govt. of Nepal Ministry of External Affairs Mechanical Electrical Plumbing Material Test Certificate Non-Conformity Report No Objection Certificate Project Execution Manual Project Management Consultant Running Account Bill School Management Committee Team Leader Tribhuvan University Central Library |
| --- | --- |

- Introduction

This Project Execution Manual (PEM) showcases the project delivery strategy for the project: “Reconstruction of School Buildings & A Library Building in Earthquake affected Districts of Nepal”

This PEM has been prepared after a thorough assessment of the contract and company’s existing Standard Operating Procedures (SOP’s). The assessment focussed on the key deliverables including identifying gaps in contract administration, project management and execution processes. Changes & improvements were identified and incorporated to develop a comprehensive plan to effectively guide project manager throughout construction project cycle & defect liability period phase. Best practices have been included to enhance the product delivery method.  This manual will act as a guideline for smooth and effective implementation of the project, clearly defining the responsibility of each entity.

The PEM includes five phases and overarching project controls. The phases are:

- Initiation

- Planning

- Construction

- Closeout

- Defect liability period

Each section includes a detailed description, checklistand a list of forms required per stage of the project.

The checklists have been developed to support project implementation and specifically identify the responsibility for key tasks. It identifies the responsible party per task, reviews/approvals, deliverables, applicable forms, and specific activities per phase. The checklists can be adjusted based on the scope of the project. The Team Leader (TL) of the PMC will consult with the DLPIU / CLPIU throughout the project regarding issues or questions that arise in execution of the project requirements.

The flow charts capture the high-level major activities within each phase. This allows the PMC team to understand the full spectrum and process per phase.

The forms have been consolidated and standardized. Each form is linked to a specific task within the checklists. This will assist the PMC team in knowing what form to fill out, why, when, and where.

- About the Project

MEA, GOI, New Delhi is the Donor and development partner for the project : Reconstruction of 70 Schools and 1 library in earthquake affected areas of Nepal.

CSIR-CBRI has been appointed as the DPMC (Design Project Management Consultant) for end-to-end construction management for the following

- Reconstruction of 70 higher secondary schools in line with GoN’s Guidelines for Developing Type Designs for School Buildings in Nepal on disaster-resilient standards, and equipped with water and sanitation facilities, including gender-specific toilets, disabled and child friendly features and science and computer laboratories

- Reconstruction of Central Library in Tribhuvan University, Kathmandu in line with disaster-resilient standards and modern amenities.

- Schools are located in the following districts of Nepal : Ramechhap, Sindhupalchowk, Nuwakot, Gorkha, Dolakha, Kavrepalchowk, Dhading & Kathmandu

Most of the buildings are RCC frame of 1, 2 or 3 storeys having 2 to12 classrooms, lab, toilet block etc. with certification from National and International organization and meeting all local, National and International codes/ norms, guidelines with utmost priority for safety and security.

The present activity assures to deliver End to End construction management consultancy services at all stages of the project, pre-construction, construction and post-construction in order to perform construction management, supervision and progress reporting of all the projects mentioned above.

Project Reporting Structure

Stakeholder Table

| STAKEHOLDERS |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Procedures / Tasks | GOI - MEA/ Ind Embassy | GON – MOEST | NRA – CLPIU(E) | NRA – DLPIU(E) | SMC / TUCL | CBRI | Contractor |
| Permit / NOC’s |  |  |  |  |  |  |  |
| Coordination |  |  |  |  |  |  |  |
| Contracting |  |  |  |  |  |  |  |
| Scheduling |  |  |  |  |  |  |  |
| Subcontracting |  |  |  |  |  |  |  |
| Procurement |  |  |  |  |  |  |  |
| Approvals |  |  |  |  |  |  |  |
| Variations |  |  |  |  |  |  |  |
| Invoicing |  |  |  |  |  |  |  |
| Monitoring |  |  |  |  |  |  |  |
| Acceptance |  |  |  |  |  |  |  |
| Closeout |  |  |  |  |  |  |  |
| DLP |  |  |  |  |  |  |  |

A stakeholder is any person or organization who can be positively or negatively affected by or cause an impact to project delivery. It is important to identify all stakeholders for the purpose of identifying their project interest and objectives.

A stakeholder analysis is performed at the start of project to clarify roles, level of engagement and impact of changes

CBRI Project Set-Up

The above figure shows the tentative deployment for the PMC Site staff.

For effective implementation of the project, PMC shall establish its office at Kathmandu, Nepal and at each district HQ.

The operations will be managed from the Kathmandu based Team Leader. Site Engineers will be deployed at sites for supervision & reporting. Their roles in various tasks in each phase are described in this manual.

The Support staff at Kathmandu office will comprise of Planning Engineer and computer expert cum document controller. There shall be visits of MEP experts to monitor the services activities.

The Team leader will supervise the Site Engineers, make periodic visit to sites and ensure the deliverables are met. The progress of work at sites will be reviewed by the team leader and submit monthly report to CLPIU.

He/she shall be the focal point for correspondence with all stakeholders.

Apart from site team, there will be a Project Management Specialist based at CSIR-CBRI Roorkee for coordinating with CLPIU.

- Processes

| Section 1 – Initiation Phase |  |  |  |
| --- | --- | --- | --- |
| S. No. | Activity | Responsibility | Record |
| - STAKEHOLDER KICK OFF MEETING |  |  |  |
| (i) | After the award of tender, Conduct kick off meeting with CBRI, CLPIU, DLPIU, Contractor etc. The following should be discussed as minimum: - CBRI Scope of works - Execution plan - Roles & responsibilities of CBRI in the project - site team – organization - Communication matrix - Reports to be submitted& timeline for submission - Information & Document required from client | PMC Team Leader | MOM |
| (ii) | Arrange following training to Team Members : - Project Orientation - Construction Methodology - Inspection & Test Plan - Inspection Methods - Any specialized item training as per site requirement Provide trainings for the contractor: - Inspection Protocol - Inspection & Test Plan - Workmanship & acceptance parameters |  |  |
| - SITE TEAM DEVELOPMENT |  |  |  |
| (i) | PMC to initiate the site team for deployment at project Names & Contact detail of Site Team to be shared with CBRI, CLPIU, DLPIU along with tentative deployment dates. | PMC Team Leader | Site Deployment Plan Organization Chart |
| - HANDOVER DOCUMENTS TO SITE TEAM |  |  |  |
| (i) | The following documents to be handed over to the site team: - MOM of kick-off meeting - Contract documents - Project Specifications | SIC | Handover docs checklist |
| - INTERNAL KICK OFF MEETING |  |  |  |
| (i) | Conduct internal kick off meeting with site team members. Following agenda should be discussed as minimum: - Project Description - Construction progress - CBRI scope - Site Team deployment - Site Facilities, Equipment, Instrument - Roles & responsibilities of team members - Tender documents review Site team should study documents prior to meeting and highlight points of concern - Client, Contractor & other stakeholders - Communication - Initial Reporting - Project Quality Plan - Inspection &Testing Plan - Any training or document requirement | TL | MOM |
| (ii) | The internal kick off meeting should clearly define the requirements; action plan & should be reviewed in subsequent meetings. | TL | MOM |

| Section 2 – Planning Phase |  |  |  |
| --- | --- | --- | --- |
| S. No. | Activity | Responsibility | Record |
| - SITE SURVEY |  |  |  |
| (i) | Conduct a site survey & prepare a comprehensive report on: - Actual status at project site - Identify logistical issues with regard to construction and/or operation - Review site boundary, building orientation, access to site - Lookout for any safety requirement | TL | Site Survey Report |
| - RISK ASSESSMENT |  |  |  |
| (i) (ii) | Identify risks related to project scope, delivery & quality To update the risk Register on a monthly basis | TL | Risk Register |
| - EXECUTION STRATEGY |  |  |  |
| (i) | Based on the documents received & initial visit to site, the following needs to be developed for successful execution: - Staff requirement for the project - Logistics - How inspections will be carried out - Site visits by TL - Reporting Matrix - Communication protocol - Site Meetings - Monthly, Quarterly Reports | TL |  |
| - STAFFING PLAN |  |  |  |
| (i) (ii) (iii) | Prepare staff deployment schedule based on inputs from client regarding the starting of new projects. Staffing plan shall comply to contractual requirements The single document shall include all the projects mentioned in the contract, and be updated regularly. | TL | Staff Deployment Plan |
| - QUALITY MANAGEMENT PLAN |  |  |  |
| (i) | While reviewing QAP or preparing a new QAP, the following protocols should be ensured as minimum: - Inspection – Work & Material How, when & by whom Inspection Request will be raised - Material approvals Whether approved materials & vendors list already exists How new materials & vendors for the project to be approved - Quantity Certification Procedure for certification of quantity - Production Plants General methodology for production from batching / asphalt plant, calibration & monitoring - Mock ups Requirements for mock ups as per contract - Non conformities Procedure for addressing non conformities - Documentation Documentation Requirements – documents, formats, records, registers - Communication Communication between PMC, Contractor & DLPIU/ CLPIU - Project Closeout List out activities & documents during completion of project | TL | Inspection flowchart Inspection request format Approved materials / suppliers list |
| - INSPECTION & TESTING PLAN |  |  |  |
| (i) | While reviewing ITP or preparing a new ITP, the following should be ensured as minimum: - Material & Work activity - Type of test required - Test frequency - Acceptance criteria / Relevant IS code / document - Checklist /Test format | TL | ITP Format |
| (ii) | Checklist & Test formats to be aligned with project requirements | TL | Checklist |
| (iii) | Approval of ITP & Checklists to be taken from client before implementing at site. |  |  |
| - DOCUMENTATION PLAN |  |  |  |
| (i) (ii) | Prepare project specific documents and formats and issue to sites for implementation. Contractor to be instructed not to alter or modify format. List down which documents / records to be maintained at: - Project site by contractor - Project site by PMC site engineer - PMC Central Office | TL | Master List Document Register |

| Section 3 – Construction Phase |  |  |  |
| --- | --- | --- | --- |
| S. No. | Activity | Responsibility | Record |
| - STAFF DEPLOYMENT |  |  |  |
| (i) (ii) (iii) (iv) | Deploy site Engineer to the designated site. In certain cases, Site Engineer will be required to handle multiple sites. Team leader to brief about the project requirements and interaction with stakeholders. Site Engineer to be provided a scope compliance sheet which enlists the tasks to be performed with respect to scope of the contract. | TL | Scope Compliance |
| - PRE-CONSTRUCTION MEETING |  |  |  |
| (i) (ii) (iii) (iv) (v) | Conduct pre construction meeting with the contractor. Discuss on the key deliverables, mobilization, monitoring strategy, billing& roles & responsibilities of PMC & Contractor. To discuss implementation of quality plan & inspection plan at sites. To hand out list of initial submittals required for the project. Requirements of drawings & other documents to start work. | TL | MOM |
| - CONTRACTOR MOBILIZATION |  |  |  |
| (i) (ii) | Contractor to arrange during site mobilization: - Permits/ NOC’s - Staff & workmen joined site - Dismantling / Preparatory works - Fencing / Boundary Requirements - Site office - Concrete plant / Mixer /Other Equipments / Machinery - Material procurement - Testing Facilities CBRI will monitor the mobilization and follow up for starting works at site | Contractor Site Engineer |  |
| - DOCUMENTATION |  |  |  |
| (i) | The following records to be maintained at site by the contractor: - Daily Works Register - Works / Material Inspection summary - Inspection Report Attach bunch of back up documents consisting of filled checklist, lab report, MTC etc. - Material Approval Register - Site Instruction Register - NCR register - Client Instruction Register - Monthly Report The following records to be maintained at site lab by the contractor: - Lab equipment’s calibration - Material test results as per approved format - Concrete cube test register | Contractor |  |
| (ii) | The following documents to be maintained at site: - Contract documents - Project Specifications - Relevant IS codes - Approved Working Drawings latest revision - Quality Assurance Plan - Inspection & Test Plan | Contractor |  |
| - DRAWING CONTROL |  |  |  |
| (i) (ii) (iii) | Review drawings during issue to site. Take feedback of Contractor & sort out any drawing related issue by coordinating with Client. Prepare drawing register and update any new revisions received for drawings. Ensure that superseded drawings are not used at site. | Site Engineer Site Engineer Site Engineer | Drawing Register |
| - SUBMITTALS |  |  |  |
| (i) (ii) (iii) | Prepare a list of submittals by the Contractor - Material Approval - Supplier / Subcontractor Approval - Daily / Monthly Reports - Quality Plan - Safety Plan - Method Statements - RFI - Change request - Invoice Contractor to use transmittal sheet for submissions. Log to be maintained PMC to review and approve after coordination with Client. | Contractor Contractor Site Engineer / TL | Transmittal Sheet / Log |
| - QUALITY MANAGEMENT |  |  |  |
| (i) (ii) (iii) (iv) (v) (vi) | Contractor to submit / comply with Quality assurance plan Approval of materials including concrete mixes to be taken prior to use at site. Contractor to undertake full responsibility for Quality. Material testing facilities to be identified – site / 3rd party lab Implement the approved ITP at site. Establish Inspection Protocol. Contractor to ensure 100% compliance. Review Lab / Equipments / Calibration. Check against contract provision Perform inspection at site – work/material/lab testing Ensure use of proper formats & checklist. PMC to monitor compliance to design, drawings & specification. Defects, workmanship issues to be notified. Issue NCR - Serious issues to quality, contractual violations. Discuss Quality Issues in weekly & Monthly meetings | TL TL Site Engineer Site Engineer Site Engineer Site Engineer | Site Lab Equipments Inspection Intimation WIR/ MIR/ Checklists NCR Report / Log MOM |
| - SITE VISITS / INSPECTION |  |  |  |
| (i) | The following information should be confirmed from the contractor & noted in Site Diary format. - Work done & qty. - Incoming construction material & qty. | Site Engineer | Daily works register |
| (ii) | Take a stock of ongoing activities. Make a site visit & following items should be checked: - Work activities follow method statement - Approved materials are used at site - Works including finished product conforming to specifications - Random visits to production plants | Site Engineer | Daily Report |
| (iii) | Attend formal inspections raised by the contractor - Field Inspection - Material Inspection - Lab Test Witness Refer to the Inspection protocol & ITP for carrying out the required inspections | Site Engineer | WIR / Checklist MIR. Test Formats NCR |
| (iv) | Apart from the above Engineer deployment, 2 scientists/ Engineers from CSIR-CBRI will also randomly check the construction activities twice in a month | CSIR-CBRI Scientist/ Engineer |  |
| - DAILY SITE REPORT |  |  |  |
| (i) | To prepare a daily site report and submit to DLPIU via online reporting app. The daily site report format shall be approved by the client & contain information about: - Man & machinery utilised - Construction activities in progress - Items inspected & approval - Quality & safety concerns Contractor to give necessary inputs to PMC for generating the report. | Site Engineer | Daily Site Report |
| - MOCK UPS / SAMPLE APPROVAL |  |  |  |
| (i) (ii) (iii) | Mock up for important items such as Electrical, Sanitary, Paint, Tiling work to be prepared and approved before proceeding at site. Contractor to prepare mock up with approved materials. One sample to be prepared for each defined items as mentioned in (i) CBRI to review mock up along with CLPIU prior to approval. | Contractor Contractor Site Engineer | Mock up register |
| - TESTING |  |  |  |
| (i) (ii) (iii) (iv) | Site lab Contractor to set up site laboratory & provision of testing equipments for tests required at site. Equipments to be in good working condition & calibrated. Contractor to conduct lab & filed testing at per approved ITP. Use approved test formats for recording test results. CBRI Site Engineer to witness tests and sign off on test results. 3rd Party Lab In case testing facility is not available at site, contractor to arrange for 3rd party lab for testing purpose. Contractor to submit the credentials / for lab for approval. | Contractor Contractor Site Engineer Contractor | Site Lab Equipments |
| - SAFETY MONITORING |  |  |  |
| (i) (ii) (iii) (iv) v) | Ask for Client's Safety Requirements. If not available, discuss with safety needs with client and freeze the safety inspection format. Contractor to ensure safety at site & conduct routine inspection Issue Unsafe Work Notice for serious safety violations with clear instructions whether work to be stopped until corrective actionor can be continued conditionally. Discuss Safety Issues in Weekly & Monthly meetings Prepare a monthly report on Safety Issues. This report to be prepared by the contractor. | TL Contractor Site Engineer Site Engineer Contractor | Safety Inspection Checklist Unsafe Work Notice/log Minutes of Meeting Monthly Safety Statistics |
| - ACTION ON NON-CONFORMITIES |  |  |  |
| (i) (ii) | Once an issue has been identified, Issue of Non conformity Report. citing the applicable clause from specification and/or IS code. Clear photos to be attached for reference. Inform client about the NC Regular follow up with contractor for close out action. Action on non-conformities to be discussed in weekly / monthly meetings. | Site Engineer (in consultation with TL) | NCR / log |
| - SUPPLIER / SUBCONTRACTOR APPROVAL |  |  |  |
| (i) (ii) | Supplier / Subcontractors to be evaluated before engaging at site; particularly finishing items, MEP specialised sub-contractors Contractor to submit supplier/ subcontractor credentials | Contractor Contractor |  |
| - CONSTRUCTION WORKS |  |  |  |
| (i) (ii) (iii) (iv) (v) | Contractor to carry out construction works as per the planned schedule. Construction method statements to be submitted for all major activities. To undertake full responsibility for compliance to specifications, quality and safety norms. Stage wise approvals to be taken before proceeding to next activity. To provide stagewise approvals and raise quality issues for corrective action | Contractor Contractor Contractor Contractor Site Engineer | WIR / Checklist WIR |
| - PROGRESS MONITORING |  |  |  |
| (i) (ii) (iii) (iv) (v) (vi) | To prepare the project baseline schedule on MSP or suitable platform as approved by the client To deduce weekly targets from schedule & track weekly progress against target. Project monthly progress report to be comprised of: - Work done against BOQ provision - Progress actual v/s planned, S curve, Variations - Baseline revision / Days delayed /NOD / EOT - Procurement status To prepare a monthly progress summary for quick reference and submit to CLPIU. To review current progress and action plan for deviations from the schedule To assist contractor in catch up plan for delays & procurement tracking for long lead items | Contractor Contractor Site Engineer Site Engineer / TL Site Engineer / TL TL | Project Schedule |
| - MEETINGS |  |  |  |
| (i) | With CLPIU, DLPIU ) - Attend meetings on a regular basis. - Items may be discussed- project progress, hindrances, variations, resources, billing - Circulate MOM to team for action - Follow up on action | TL | MOM |
| (ii) | With Contractor - Plan a weekly meeting at site with key contractor’s personnel - Agenda to be followed: progress update, targets, quality, safety, compliance of comments, testing of materials & concrete elements - Raise other areas of concern - File MOM for records & review action status | Site Engineer | MOM |
| (iii) | Internal - Review with site team project status - Inspection related issues & solutions - Any areas of concern - File MOM for records &review action status | TL | MOM |
| - REQUEST FOR INFORMATION |  |  |  |
| (i) (ii) | Contractor to raise Request for Information for seeking clarity on the matters relating to drawings, specifications, services / systems, etc. CBRI to review & coordinate with Client for response. | Contractor TL | RFI |
| - QUANTITY CERTIFICATION |  |  |  |
| (i) (ii) (iii) (iv) | Contractor to maintain quantity measurements on MB / proforma as approved by the client. Site Engr to certify 100 % quantity measurements. Review status on weekly basis. Measurements shall be checked with contractors & DLPIU and shall be accompanied with detailed sketches and quantification. Team Leader to verify / review / check at least 25% measurements including hidden measurements. | Contractor Site Engineer TL | Measurement Book |
| - PROCESSING OF BILLS |  |  |  |
| (i) (ii) (iii) (iv) (v) (vi) (vii) (viii) | A protocol for invoicing & payments to be finalised at site. It shall conform to Clients directive. Target dates to be set for: - submission of RA / Final Bill by the contractor - review and submission of bill to Client RA bills to be submitted by contractor. RA bills to be attached with back up documents like signed Joint measurement sheets, approved MIR, WIR, test reports, checklists, etc. as desired by the Client. Check contents of RA bills. Revert to contractor for any deficiencies / flaws The documents need to be furnished by the contractor during the submission of their Running Account bills are mentioned as below: - Contract Document (in case of 1st R.A bill) - Work Order (in case of 1st R.A Bill) - IPS (Interim Payment Sheets/Running Bills) or Abstract sheets - Bank Guarantee (in case of 1st RA bill) - Recommendation Letter from PMC Team Leader The typical Billing Cycle is given below: Contractor BillSite Verification by PMC or resident engineer DLPIUCLPIU Keep a watch on the billing for the month, cumulative billing against project budget Look at the provision in contract for variations in qty. in overall & individual items Variations/ Extra items billing to follow client's directives To coordinate with Client for approval & release of payment. | TL TL Contractor Site Engineer / TL TL TL TL TL |  |
| - PROJECT REPORTING |  |  |  |
| (i) (ii) (iii) (iv) | Weekly Report to be prepared as per the approved format. For Each Project, contractor to prepare monthly / quarterly report summarising the following: - Progress - planned v/s actual, Hindrances, NOD/EOT, Baseline revision, Proposed changes - Commercial - billing, payments, variations - Quality - compliance & issues - Safety - compliance & issues - Compliance certification with evidences PMC will develop the structure of the report based on the contractual requirements. Contractor to compile all the data for the report. PMC to review the report and submit to CLPIU by first week of next month. | Contractor Site Engineer Contractor Site Engineer | Weekly Report Monthly / Quarterly Report |
| - MOTIVATION AWARDS |  |  |  |
| (i) | Programmes like appreciation & awards will be organised regularly to motivate the project team. Best performing engineers from PMC and contractor will be recognised for dedication & quality service and awarded by CBRI/ CLPIU monthly. | TL in discussion with CBRI/ CLPIU |  |

Section 4 – Closeout Phase

| S. No. | Activity | Responsibility | Record |
| --- | --- | --- | --- |
| - CLOSE-OUT CHECKLIST |  |  |  |
| (i) (ii) | Prepare list of activities / tasks to be performed for the project close-out and taking over by the client Contractor to plan the activities for close-out. | TL (assisted by Site Engineer) | Closeout Checklist |
| - MEP TESTING & COMMISIONING |  |  |  |
| (i) | Testing & Commissioning for MEP services to be carried for all identified items. | Contractor | Commissioning Report |
| - FINAL INSPECTION |  |  |  |
| (i) | Make a final inspection of the completed project – Structural, Finishing & MEP Services works. The punch list will comprise of: - Pending works - Defective works - Pending action for NCR’s Contractor to do the corrective action & raise inspection for rectified snags. To review snags & update the Punch List | Site Engineer Contractor Site Engineer | Punch List |
| - HANDING OVER DOCUMENTS |  |  |  |
| (i) | PMC to confirm the handing over documents from the CLPIU & prepare the final documents handing over checklist. The following documents may be considered: Inspection reports & supporting documents - Measurement sheets - NCR closure - Client Instruction Register - Final Punchlist closure - Client communications - As built drawings - O&M Manuals & Warranty Certificates | TL | Checklist |
| (ii) (iii) | Handing over documents to be compiled & submitted to client. Archiving of documents in hard & soft copies to be ensured. | Site Engineer |  |
| - AS-BUILT DRAWINGS |  |  |  |
| (i) (ii) (iii) (iv) (v) (vi) (vii) (viii) | The contractor shall submit the list, schedule & parties responsible for the as-built drawings – Structural, Architectural & MEP. The final revision approved drawings to be sent to responsible parties ( Contractor’s internal team members/ subcontractor) for checking compliances. Any amendments to the approved drawings to be highlighted. The Amendment in the drawings to be checked jointly by the Contractor & Site Engineer (PMC) Contractor to and submit the as-built drawings including amended drawings to PMC for review & approval. PMC to review as-built drawings & accord approval by signing on as-built drawing stamp The contractor to maintain as-built status list to track the progress of as-built drawing submissions. Contractor to preserve the as-built drawing copies and hand over to PMC in documents handing over process. PMC will submit the As-built drawings to CLPIU | Contractor Contractor Contractor / Site Engineer Contractor Site Engineer Contractor Contractor Site Engineer | As-built drawing schedule As built drawing schedule |
| - FINAL ACCEPTANCE |  |  |  |
| (i) | Upon closure of snags & receipt of handing over documents, coordinate with Client for issuing taking over certificate. Contractor to be instructed for complete de-mobilization from the site. | TL | Taking over certificate |
| (ii) | Prepare project completion report Summarize key take-offs from the project including lessons learnt with reference to project execution & contractor performance for awareness & improvement. | TL Assisted by Site Engineer | Project Completion Report |
| Section 5 – Defect Liability Phase |  |  |  |
| S. No. | Activity | Responsibility | Record |
| - DEFECT LIABILITY PERIOD NOTIFICATION |  |  |  |
| (i) (ii) | To identify all stakeholders with the help of Client and their role clarity & interaction during Defect Liability Period To Notify all stakeholders of the starting of Defect Liability Period for handed over project. This will be done after prior approval by Client | TL (assisted by Site Engineer) TL | TOC (Notification by mail) |
| - SITE VISIT |  |  |  |
| (i) (ii) (iii) (iv) (v) (vi) (vii) | To submit a plan for routine joint inspection with contractor & end user. To attend defect intimation by client for immediate resolution To conduct inspection as per plan covering all the areas in the facility. Action performed on snags notified earlier to be verified. Submit inspection report to the contractor/client & follow up for rectification. Contractor to do rectification for identified defects and apprise PMC. To maintain defects register and update as rectification is completed. To notify Client on the status of DLP on a regular basis | Site Engineer Site Engineer Site Engineer Site Engineer Contractor Site Engineer Site Engineer | Inspection Plan Inspection Report Defects Register Monthly Report |
| - INSPECTION REPORT |  |  |  |
| (i) | Inspection report shall provide information on: - Type of defect - Location - Any repair instruction - Priority | Site Engineer | DLP inspection report |
| - HANDING OVER DOCUMENTS |  |  |  |
| (i) | PMC to check the handing over documents checklist. The following documents may be considered: - Inspection reports & supporting documents - Measurement sheets - NCR closure - Client Instruction Register - Final Punchlist closure - Client communications - As-built drawings The As-built drawings submitted during project construction completion to be reviewed again for any changes. If any change is observed, drawing to be revised. - O&M Manuals & Warranty Certificates | Site Engineer / TL | Checklist |
| (ii) (iii) | Handing over documents to be compiled & submitted to client. Archiving of documents in hard & soft copies to be ensured. | Site Engineer |  |
| - CLOSEOUT |  |  |  |
| (i) | CBRI to notify closure of DLP. To submit status of any pending defect repair works to the CLPIU. | TL |  |
| (ii) | To ensure all documents handing over process to client is completed. | Site Engineer |  |

- Inspection Protocol

GENERAL - Inspection and Test Plan (ITP) to be prepared for all activities in the project and approved by Client. - Material inspection: Materials for construction including raw material for concrete will be tested as per the approved ITP. Records of Material Inspection approval along with backing documents such as MTC, Site / 3rd party Lab Test Report to be maintained. - Work inspection: Inspection carried out at various stages of work as per approved ITP. Records of in process work inspection along with backing documents checklists, field & lab test reports to be maintained. - Checklists for inspection and testing activities are available as part of the standard set of forms. These checklists are to be modified as appropriate depending on project specific conditions and utilized where applicable and approved by client GUIDELINE FOR ROUTINE WORK - A good coordination has to be done within team & contractor. - The Approved ITP, checklist & test formats to be forwarded & discussed with the Contractor at the earliest. - Contractor to send an Intimation of Inspections for the next day – material, work & testing - A format has been provided for intimation of Inspection - Upon receiving Intimation from all assigned sites, PMC Site Engineer will Plan visit schedule for the next day and update Contractor on his visit plan. - Contractor to coordinate with PMC Site Engineer for inspection at site. Contractor to keep the IR forms, checklist, drawings ready at the time of inspection - PMC Site Engineer will perform the inspections & sign on IR, checklist & tests. - Contractor will retain the originals and provide copy to PMC Site Engineer for reference. - PMC Site Engineer will upload the Inspection Report in the Mobile App - Daily Inspection Reports will be monitored in the Mobile App based reporting system. - Team Leader has to monitor performance of PMC Site Engineers on a weekly basis.

Work Inspection Submittal & Approval Process

Material Inspection Submittal & Approval Process

- Mobile App based Reporting for Daily Monitoring

A system for mobile based project reporting by field engineers and a web-based dashboard for view of such daily reports by project stakeholders is outlined below.

The key implementation aspects for the monitoring system are as follows:

- Offline data entry capability on mobile in absence of mobile networks.

- Support for multiple forms/ proforma on mobile

- Custom dashboard for report viewing and user management

- Admin based report approval mechanism.

- Summary daily project progress report.

Overall Information Flow

Mobile Reports data capture formats

Engineers in the field will use the mobile app to fill in daily work reports. They will select the school project from the drop-down menu in the app.

The App will consist of 2 sections:

A. Daily Report. Here Site Engineer will fill the data related to :

  - General info ( Weather , manpower, Equipment)

  - Incoming Construction Material

  - Construction Activities

  - Testing ( field& lab)

  - Photographs

B. Site Issues

-       Any observation, non-compliance to be entered here.

The user will be able to raise & close the issues by logging to this section.

It is envisioned that the above daily activities be shown as compiled in form of a single report for the day. The App will allow input data in simple form that can be filled individually at any time. The server will compile the final report automatically.

Output.

- The Daily Report Will Be Presented In The Approved Format.

| Name of Work |  | Reconstruction of 70 school building and 2 Library Facilities in earthquake affected districts of Nepal |  |  |  | Date |  |  | 01.02.2020 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Site |  | Tara Uchhater Madhyamik Vidyalaya, Gorkha |  |  |  | EMIS Code |  |  | (EMIS Code 360500018) |  |
| Structural Detail |  | RCC Framed Structure |  |  |  | Grade of Steel |  |  | Fe-500 |  |
| Concrete |  | Nominal Mix |  |  |  | Drawing Title & No. |  |  | TC(M or S) |  |
| Contracting Agency |  | A&B JBV |  |  |  |  |  |  |  |  |
| Project Start Date |  | 1 JAN 2018 |  |  |  | Project End Date |  |  | 3 March 2020 |  |
| Name of Site In-Charge |  |  |  |  |  | Name of School Representative |  |  |  |  |
| Type of Building |  | 3S9C Building Block |  |  |  | Name of DLPIU Staff if any |  |  |  |  |
| Weather |  | Sunny /Cloudy/Rainy/Windy |  |  |  |  |  |  |  |  |
| Ambient Temperature oc |  | Max./Min. |  |  |  |  |  |  |  |  |
| Contractor’s Manpower |  |  |  |  | Plant & Equipment I= Idle B=Breakdown |  |  |  |  |  |
| Category | No. |  | Category | No. | Type |  | QTY | Hours Worked |  | Status |
| Project Manager |  |  | Labour |  | Backhoe |  |  |  |  |  |
| Engineer |  |  | Skilled |  | Wheel Loader |  |  |  |  |  |
| Foreman |  |  | Unskilled |  | Tipper |  |  |  |  |  |
| Technician |  |  |  |  | Roller Compactor |  |  |  |  |  |
| Operator |  |  |  |  | Mobile Crane |  |  |  |  |  |
|  |  |  |  |  | Tower Crane |  |  |  |  |  |
| Subcontractor’s Manpower |  |  |  |  | Transit Mixers |  |  |  |  |  |
| Subcontractor Name |  |  | Category | No. | Concrete Pump |  |  |  |  |  |
|  |  |  |  |  | Welding Machine |  |  |  |  |  |
|  |  |  |  |  | Generator |  |  |  |  |  |
|  |  |  |  |  | Bar Bending Machine |  |  |  |  |  |
|  |  |  |  |  | Concrete Batching Plant |  |  |  |  |  |

| MATERIALS RECEIVED AT SITE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| S.No. | Item | Unit |  | Qty. | Accepted/ Rejected |
| CONSTRUCTION ACTIVITIES |  |  |  |  |  |
| S.No. | Location | Activity |  | Qty. |  |
| TEST CONDUCTED AT SITE |  |  |  |  |  |
| S.No. | Location | Activity |  | Qty. |  |
| ANY OTHER OBSERVATION ON QUALITY/PROGRESS/ SAFETY |  |  |  |  |  |
| DAILY REPORT - PHOTOGRAPHS |  |  |  |  |  |
| Photo 1: |  |  | Photo 2: |  |  |
| Photo 3: |  |  | Photo 4: |  |  |

| Contractor (Name) Signature Date: | Consultant (Name) Signature Date: |
| --- | --- |

2. A log of Site Issues that will be updated regularly.

The log will look like as given below.

Dashboard and Report View

A website with access control will be created for viewing the reports.

The dashboard in the website will give a statistical / pictorial presentation on the inspection visits.

The dashboard for report viewing will have 3 role based authorization for specific permissions as follows.

Admin Role	: User management, master data add/ edit/ assignment to users in addition toreports viewing.

Manager Role	: Viewing individual reports, report approval for general availability

Viewer Role	: Basic report viewing permission only limited to daily summary report

Mobile User Site Allocation

Projects listing by location

Daily Reports view in PDF format

Geo Mapped Reports

Metrics & KPI’s on Dashboard

---------------------------------- END OF DOCUMENT ----------------------------------